## EMS
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Airline Reservation System | 1 | Login | Analysis | Requirement Analysis | 2 | 2016-11-24 | 2016-11-24 | 2 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-24 | 2016-11-24 | 3 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-24 | 2016-11-24 | 1 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-26 | 2016-11-26 | 4 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 2 | 2016-11-24 | 2016-11-24 | 1.5 | 2016-11-24 | 2016-11-24 | Sapana Mishra | Completed
|  |  |  | LLD Preparation | 2 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Sapana Mishra | Completed
|  |  |  | UTP Review | 1 | 2016-11-25 | 2016-11-25 | 0.5 | 2016-11-25 | 2016-11-25 | Samarth | Completed
|  |  |  | UTP Rework | 1 | 2016-11-25 | 2016-11-25 | 0.5 | 2016-11-25 | 2016-11-25 | Sapana Mishra | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-26 | 2016-11-26 | 0.5 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | LLD Rework | 1 | 2016-11-26 | 2016-11-26 | 0.5 | 2016-11-26 | 2016-11-26 | Sapana Mishra | Completed
|  |  | Build | Coding | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Code Self Review | 1 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Self Testing | 1 | 2016-11-25 | 2016-11-25 | 1 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Rework | 1 | 2016-11-25 | 2016-11-25 | 0.5 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | Peer Testing | 2 | 2016-11-25 | 2016-11-25 | 1 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | Test Result review | 1 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Rework | 1 | 2016-11-25 | 2016-11-25 | 0.5 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Code Integration | 2 | 2016-11-26 | 2016-11-26 | 3 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-11-26 | 2016-11-26 | 3 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 35.5 |  | Total Actual Hrs:
Airline Reservation System | 2 | Registration | Analysis | Requirement Analysis | 2 | 2016-11-24 | 2016-11-24 | 2 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-24 | 2016-11-24 | 3 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-24 | 2016-11-24 | 1 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-24 | 2016-11-24 | 4 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 2 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Tanu Verma | Completed
|  |  |  | LLD Preparation | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Tanu Verma | Completed
|  |  |  | UTP Review | 1 | 2016-11-25 | 2016-11-25 | 0.5 | 2016-11-25 | 2016-11-25 | Nupur Atray | Completed
|  |  |  | UTP Rework | 1 | 2016-11-25 | 2016-11-25 | 1 | 2016-11-25 | 2016-11-25 | Nupur Atray | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-26 | 2016-11-26 | 0.5 | 2016-11-26 | 2016-11-26 | Tanu Verma | Completed
|  |  |  | LLD Rework | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Nupur Atray | Completed
|  |  | Build | Coding | 5 | 2016-11-25 | 2016-11-25 | 6 | 2016-11-25 | 2016-11-25 | Tanu Verma | Completed
|  |  |  | Code Self Review | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | Self Testing | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | Rework | 2 | 2016-11-26 | 2016-11-26 | 1.5 | 2016-11-26 | 2016-11-26 | Ity Mehta | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Ity Mehta | Completed
|  |  |  | Peer Testing | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Test Result review | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Rework | 2 | 2016-11-26 | 2016-11-26 | 2.5 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Code Integration | 2 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 43.5 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 3 | Change Password | Analysis | Requirement Analysis | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-26 | 2016-11-26 | 3 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 3 | 2016-11-26 | 2016-11-26 | 2.5 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | LLD Preparation | 3.5 | 2016-11-26 | 2016-11-26 | 3.5 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | UTP Review | 1 | 2016-11-26 | 2016-11-26 | 0.5 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | UTP Rework | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Sapna Mishra | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-28 | 2016-11-28 | 0.5 | 2016-11-28 | 2016-11-28 | Samarth | Completed
|  |  |  | LLD Rework | 1.5 | 2016-11-28 | 2016-11-28 | 1.5 | 2016-11-28 | 2016-11-28 | Samarth | Completed
|  |  | Build | Coding | 3 | 2016-11-26 | 2016-11-26 |  | 2016-11-26 | 2016-11-26 | Tanu Verma | Completed
|  |  |  | Code Self Review | 1 | 2016-11-26 | 2016-11-26 |  | 2016-11-26 | 2016-11-26 | Tanu Verma | Completed
|  |  |  | Self Testing | 1 | 2016-11-26 | 2016-11-26 |  | 2016-11-26 | 2016-11-26 | Tanu Verma | Completed
|  |  |  | Rework | 0.5 | 2016-11-26 | 2016-11-26 |  | 2016-11-26 | 2016-11-26 | Tanu Verma | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Karan Gupta | Completed
|  |  |  | Peer Testing | 2 | 2016-11-26 | 2016-11-26 | 1.5 | 2016-11-26 | 2016-11-26 | Karan Gupta | Completed
|  |  |  | Test Result review | 2 | 2016-11-26 | 2016-11-26 |  | 2016-11-26 | 2016-11-26 | Karan Gupta | Completed
|  |  |  | Rework | 3 | 2016-11-27 | 2016-11-27 |  | 2016-11-27 | 2016-11-27 | Tanu verma | Completed
|  |  |  | Code Integration | 2 | 2016-11-27 | 2016-11-27 | 3 | 2016-11-27 | 2016-11-27 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-11-27 | 2016-11-27 | 1 | 2016-11-27 | 2016-11-27 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-11-27 | 2016-11-27 | 3 | 2016-11-27 | 2016-11-27 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-11-27 | 2016-11-27 | 1 | 2016-11-27 | 2016-11-27 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 42 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 4 | Search Flight | Analysis | Requirement Analysis | 2 | 2016-11-24 | 2016-11-24 | 2 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-24 | 2016-11-24 | 3 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-24 | 2016-11-24 | 1 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-24 | 2016-11-24 | 4 | 2016-11-24 | 2016-11-24 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | LLD Preparation | 2 | 2016-11-25 | 2016-11-25 | 2 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | UTP Review | 1 | 2016-11-25 | 2016-11-25 | 1 | 2016-11-25 | 2016-11-25 | Ity Mehta | Completed
|  |  |  | UTP Rework | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Ity Mehta | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-26 | 2016-11-26 | 0.5 | 2016-11-26 | 2016-11-26 | Karan Gupta | Completed
|  |  |  | LLD Rework | 1 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Karan Gupta | Completed
|  |  | Build | Coding | 5.5 | 2016-11-25 | 2016-11-25 | 5 | 2016-11-25 | 2016-11-25 | Karan Gupta | Completed
|  |  |  | Code Self Review | 2 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Nupur Atray | Completed
|  |  |  | Self Testing | 2 | 2016-11-25 | 2016-11-25 | 1.5 | 2016-11-25 | 2016-11-25 | Nupur Atray | Completed
|  |  |  | Rework | 2 | 2016-11-25 | 2016-11-25 | 1 | 2016-11-25 | 2016-11-25 | Nupur Atray | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Nupur Atray | Completed
|  |  |  | Peer Testing | 1.5 | 2016-11-26 | 2016-11-26 | 2 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Test Result review | 0.5 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Rework | 2 | 2016-11-26 | 2016-11-26 | 1 | 2016-11-26 | 2016-11-26 | Samarth | Completed
|  |  |  | Code Integration | 2 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 41.5 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 5 | Add Passenger | Analysis | Requirement Analysis | 2 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-28 | 2016-11-28 | 4 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2016-11-29 | 2016-11-29 | 1.5 | 2016-11-29 | 2016-11-29 | Karan Gupta | Completed
|  |  |  | LLD Preparation | 2 | 2016-11-29 | 2016-11-29 | 2 | 2016-11-29 | 2016-11-29 | Karan Gupta | Completed
|  |  |  | UTP Review | 1 | 2016-11-29 | 2016-11-29 | 0.5 | 2016-11-29 | 2016-11-29 | Tanu Verma | Completed
|  |  |  | UTP Rework | 1 | 2016-11-29 | 2016-11-29 | 1 | 2016-11-29 | 2016-11-29 | Karan Gupta | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-30 | 2016-11-30 | 0.5 | 2016-11-30 | 2016-11-30 | Tanu Verma | Completed
|  |  |  | LLD Rework | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Karan Gupta | Completed
|  |  | Build | Coding | 3 | 2016-11-29 | 2016-11-29 | 4 | 2016-11-29 | 2016-11-29 | Samarth | Completed
|  |  |  | Code Self Review | 1 | 2016-11-29 | 2016-11-29 | 0.5 | 2016-11-29 | 2016-11-29 | Samarth | Completed
|  |  |  | Self Testing | 1 | 2016-11-29 | 2016-11-29 | 1 | 2016-11-29 | 2016-11-29 | Samarth | Completed
|  |  |  | Rework | 2 | 2016-11-29 | 2016-11-29 | 1 | 2016-11-29 | 2016-11-29 | Tanu Verma | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-30 | 2016-11-30 | 1.5 | 2016-11-30 | 2016-11-30 | Samarth | Completed
|  |  |  | Peer Testing | 2 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Samarth | Completed
|  |  |  | Test Result review | 2 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Tanu Verma | Completed
|  |  |  | Rework | 3 | 2016-11-30 | 2016-11-30 | 2.5 | 2016-11-30 | 2016-11-30 | Samarth | Completed
|  |  |  | Code Integration | 2 | 2016-11-30 | 2016-11-30 | 3 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 40 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 6 | Confirm Booking | Analysis | Requirement Analysis | 2 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2016-11-30 | 2016-11-30 | 3 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-30 | 2016-11-30 | 4 | 2016-11-30 | 2016-11-30 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2016-11-30 | 2016-11-30 | 3 | 2016-11-30 | 2016-11-30 | Tanu Verma | Completed
|  |  |  | LLD Preparation | 1.5 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Tanu Verma | Completed
|  |  |  | UTP Review | 1 | 2016-11-30 | 2016-11-30 | 0.5 | 2016-11-30 | 2016-11-30 | Sapana Mishra | Completed
|  |  |  | UTP Rework | 1 | 2013-12-13 | 2013-12-13 | 1 | 2013-12-13 | 2013-12-13 | Tanu Verma | Completed
|  |  |  | LLD Review | 1.5 | 2016-12-01 | 2016-12-01 | 0.5 | 2016-12-01 | 2016-12-01 | Sapana Mishra | Completed
|  |  |  | LLD Rework | 1.5 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Tanu Verma | Completed
|  |  | Build | Coding | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | Code Self Review | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | Self Testing | 0.5 | 2016-11-30 | 2016-11-30 | 0.5 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | Rework | 0.5 | 2016-11-30 | 2016-11-30 | 0.5 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | Code Peer Review | 2 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Ity Mehta | Completed
|  |  |  | Peer Testing | 2 | 2016-12-01 | 2016-12-01 | 1.5 | 2016-12-01 | 2016-12-01 | Ity Mehta | Completed
|  |  |  | Test Result review | 2 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Ity Mehta | Completed
|  |  |  | Rework | 3 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Ity Mehta | Completed
|  |  |  | Code Integration | 2 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-12-02 | 2016-12-02 | 3 | 2016-12-02 | 2016-12-02 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-12-02 | 2016-12-02 | 1 | 2016-12-02 | 2016-12-02 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 36 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 7 | Cancel Flight | Analysis | Requirement Analysis | 3 | 2016-11-28 | 2016-11-28 | 3 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2 | 2016-11-28 | 2016-11-28 | 2 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-11-28 | 2016-11-28 | 1 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-11-28 | 2016-11-28 | 4 | 2016-11-28 | 2016-11-28 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 2 | 2016-11-30 | 2016-11-30 | 2 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | LLD Preparation | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | UTP Review | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Karan Gupta | Completed
|  |  |  | UTP Rework | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Nupur Atray | Completed
|  |  |  | LLD Review | 1.5 | 2016-11-30 | 2016-11-30 | 0.5 | 2016-11-30 | 2016-11-30 | Karan Gupta | Completed
|  |  |  | LLD Rework | 1 | 2016-11-30 | 2016-11-30 | 1 | 2016-11-30 | 2016-11-30 | Ity Mehta | Completed
|  |  | Build | Coding | 2 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Sapana Mishra | Completed
|  |  |  | Code Self Review | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Sapana Mishra | Completed
|  |  |  | Self Testing | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Sapana Mishra | Completed
|  |  |  | Rework | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Sapana Mishra | Completed
|  |  |  | Code Peer Review | 2 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Tanu Verma | Completed
|  |  |  | Peer Testing | 2 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Tanu Verma | Completed
|  |  |  | Test Result review | 2 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Ity Mehta | Completed
|  |  |  | Rework | 3 | 2016-12-01 | 2016-12-01 | 2 | 2016-12-01 | 2016-12-01 | Ity Mehta | Completed
|  |  |  | Code Integration | 2 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 37.5 |  | Total Actual Hrs:
E-Commerce (Online Shopping) | 8 | View Status | Analysis | Requirement Analysis | 3 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing understanding Document & Reverse Presentation | 2 | 2016-12-01 | 2016-12-01 | 3 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Preparing QFB | 1 | 2016-12-01 | 2016-12-01 | 1 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2016-12-01 | 2016-12-01 | 4 | 2016-12-01 | 2016-12-01 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  | Design | Unit Test Plan Preparation | 2 | 2016-12-02 | 2016-12-02 | 2 | 2016-12-02 | 2016-12-02 | Samarth | Completed
|  |  |  | LLD Preparation | 3.5 | 2016-12-02 | 2016-12-02 | 2 | 2016-12-02 | 2016-12-02 | Samarth | Completed
|  |  |  | UTP Review | 1 | 2016-12-02 | 2016-12-02 | 0.5 | 2016-12-02 | 2016-12-02 | Karan Gupta | Completed
|  |  |  | UTP Rework | 1 | 2016-12-02 | 2016-12-02 | 1 | 2016-12-02 | 2016-12-02 | Samarth | Completed
|  |  |  | LLD Review | 1.5 | 2016-12-03 | 2016-12-03 | 1 | 2016-12-03 | 2016-12-03 | Karan Gupta | Completed
|  |  |  | LLD Rework | 1 | 2016-12-03 | 2016-12-03 | 0 | 2016-12-03 | 2016-12-03 | Samarth | Completed
|  |  | Build | Coding | 3 | 2016-12-02 | 2016-12-02 | 3 | 2016-12-02 | 2016-12-02 | Sapana Mishra | Completed
|  |  |  | Code Self Review | 0.5 | 2016-12-02 | 2016-12-02 | 0.5 | 2016-12-02 | 2016-12-02 | Sapana Mishra | Completed
|  |  |  | Self Testing | 0.5 | 2016-12-02 | 2016-12-02 | 0.5 | 2016-12-02 | 2016-12-02 | Sapana Mishra | Completed
|  |  |  | Rework | 1 | 2016-12-02 | 2016-12-02 | 1 | 2016-12-02 | 2016-12-02 | Sapana Mishra | Completed
|  |  |  | Code Peer Review | 2 | 2016-12-02 | 2016-12-02 | 2 | 2016-12-02 | 2016-12-02 | Ity Mehta | Completed
|  |  |  | Peer Testing | 1 | 2016-12-03 | 2016-12-03 | 1 | 2016-12-03 | 2016-12-03 | Ity Mehta | Completed
|  |  |  | Test Result review | 2 | 2016-12-03 | 2016-12-03 | 2 | 2016-12-03 | 2016-12-03 | Ity Mehta | Completed
|  |  |  | Rework | 1 | 2016-12-03 | 2016-12-03 | 1 | 2016-12-03 | 2016-12-03 | Ity Mehta | Completed
|  |  |  | Code Integration | 2 | 2016-12-03 | 2016-12-03 | 3 | 2016-12-03 | 2016-12-03 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Integration Testing | 1 | 2016-12-03 | 2016-12-03 | 1 | 2016-12-03 | 2016-12-03 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Rework | 2 | 2016-12-03 | 2016-12-03 | 3 | 2016-12-03 | 2016-12-03 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Test Result review | 1 | 2016-12-03 | 2016-12-03 | 1 | 2016-12-03 | 2016-12-03 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Total Planned Hrs : | 37 |  | Total Actual Hrs:
|  | Presentation Preparation |  | Presentation Preparation | 4 | 2016-12-03 |  | 4 | 2016-12-05 | 2016-12-05 | Karan Gupta,Samarth,Nupur Atray,Ity Mehta,Tanu Verma,Sapana Mishra | Completed
|  |  |  | Deployment | 1